## Test Cases
Product Name |  | Probashi App | TC Start Date | 2023-11-07 | TC Execution Start Date |  | TEST CASE SUMMARY
Module Name |  | Registration, Login , Suggestions | TC End Date | 2023-12-07 | TC Execution End Date |  | PASS | 0
Epic |  |  | Test Case Developed By | RAFIUL ISLAM | Web/App | Android App | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) |  | WARNING | 0
Test Executed by | [6 empty] | TOTAL | 0
Test Case ID/Name | Test Case Description | precondition | Test Data | Step Description | Expected Result | Actual | Status | Remarks
TC001 | Check Sign Up with invalid Data for Phone Number. | Go to the app | Invalid Phone num: any 10 Digit given | >Goto the app >Click SignUp >Enter Invalid Phone num | It should warn as invalid phone number. | It can not detect the invalid phone number accurately. | FAIL | Photo
TC002 | Check Sign Up with invalid Data for Full name | Go to the app | Any Invalid name | >Goto the app >Click SignUp >Enter Invalid Name as "a" | It should warn as invalid Name. | It can not detect the invalid Name. | FAIL | Photo
TC003 | Check Sign Up with invalid Data for Bangla Name | Go to the app | Any Invalid bangla name | >Goto the app >Click SignUp >Enter Invalid bangla name as "a" or any other thing | It should warn as invalid Bangla Name. | It can not detect the invalid Bangla Name. | FAIL | Photo
TC004 | Check Sign Up with invalid Data for email | Go to the app | take imput as: @kmail.c , @gmail.kom | >Goto the app >Click SignUp >Enter Invalid emaill | It should not procced. | It has started working. | FAIL | Photo
TC005 | Check Sign Up with Password, | Go to the app | Input Password | >Goto the app >Click SignUp >Enter Password | It will show password strength. | It is working fine. | PASS
TC006 | Check sign up with google | Go to the app |  | >Goto the app >Click SignUp >Click Google | It should Sign Up Successfully. | Sign Up Successfully. | PASS
TC007 | Check sign up with Facebook. | Go to the app |  | >Goto the app >Click SignUp >Click Facebook | It should Sign Up Successfully. | It does not work. | FAIL | Photo
TC008 | Check sign up with Linkedin | Go to the app |  | >Goto the app >Click SignUp >Click Linkedin | It should Sign Up Successfully. | Sign Up Successfully. | PASS
TC009 | Verify that all required fields (full name, full name in Bangla, email, password, Confirm Password) are displayed on the sign-up page | Go to the app |  | >Goto the app >Click SignUp | It should show desire contents and options. | It is working fine. | PASS
TC010 | Verify that all required fields (full name, full name in Bangla, email, password, Confirm Password) are displayed on the sign-in page | Go to the app |  | >Goto the app >Click SignIn | It should show desire contents and options. | It is working fine. | PASS
TC011 | Login with invalid data | Go to the app | any invalid / unregistered mail | >Goto the app >Click SignIn | It should not procced. | It does not work. | PASS
TC012 | Log in with Facebook | Go to the app |  | >Goto the app >Click SignIn | It should work. | It does not work. | FAIL | Photo
TC013 | Warning check for invalid input | Go to the app |  | >Goto the app >Click SignIn | It should warn. | It can not warn for all | WARNING | Photo
TC014 | Sign In with google | Go to the app |  | >Goto the app >Click SignIn >Click Google | It should work. | It does not work. | FAIL | Photo
TC015 | Settings check | Go to the app |  | >Goto the app >Click SignIn >Profile Settings >Contact Us | It should work. | It does not work. | FAIL | Photo
TC016 | Check Language Settings | Go to the app | Change Language ENG to BAN | >Goto the app >Click SignIn >Profile Settings >Language | It should work. | It does not work and let not the user to stay in the app. | FAIL | Photo
TC017 | Check Socia media Links | Go to the app | Check all social media links | >Goto the app >Click SignIn >Profile Settings >Social media | It should work. | it takes invalid links. | FAIL | Photo
TC018 | Check inputs for Sign in | Go to the app |  |  |  | All the problem remain same as signup | FAIL | Photo
Suggestion 19 | Check all the options | Go to the app | >How we can get in touch >Social media links |  | This options should be improved. Should be click able and contect should be there.
Suggestion 20 | withdraw Balance |  |  |  | It contains 20$ for a weak profile like mine. It should be checked.
Suggestion 21 | User friendly check |  |  |  | The app is not user friendly and user experience does not seem good.
Suggestion 22 | Design |  |  |  | App's Login page design is fine , but inside app, the design is not that much perfect.